## Study Plan App - Burndown Chart
Task | Start Pts | Pts Done Sprint 1.0 | Pts Done Sprint 1.5 | Pts Done Sprint 2.0 | Pts Done Sprint 2.5 | Pts Done Sprint 3.0 | Pts Done Sprint 3.5 | Pts Done Sprint 4.0 | Pts Done Sprint 4.5 | Total Pts Done
1. Create Database | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4
2. Create Documentation | 3 | 2 | 0 | 0 | [5 empty] | 2
3. Create the Main page GUI. | 4 | 1 | 1 | 1 | [5 empty] | 3
4. Create a save function. | 4 | 0 | 0 | 0 | [5 empty] | 0
5. Create Single sign-on authentication | 6 | 0 | 0 | 0 | [5 empty] | 0
6. Create a log-in page | 4 | 0 | 0 | 0 | [5 empty] | 0
7. Create eligibility function | 2 | 0 | 0 | 0 | [5 empty] | 0
8. Create Main page functionality | 3 | 0 | 0 | 0 | [5 empty] | 0
Actual Remaining Effort | 30 | 26 | 23 | 21 | 21 | 21 | 21 | 21 | 21
Estimated Remaining Effort | 30 | 26.25 | 22.5 | 18.75 | 15 | 11.25 | 7.5 | 3.75 | 0