## Study Plan App - Burndown Chart
Task | Start Pts | Pts Done Sprint 1.0 | Pts Done Sprint 1.5 | Pts Done Sprint 2.0 | Pts Done Sprint 2.5 | Pts Done Sprint 3.0 | Pts Done Sprint 3.5 | Pts Done Sprint 4.0 | Pts Done Sprint 4.5 | Total Pts Done
1. Create Database | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4
2. Create Documentation | 5 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 5
3. Create the Main page GUI. | 7 | 1 | 1 | 1 | 0 | 1 | 2 | 1 | 0 | 7
4. Create a save function. | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
5. Create Single sign-on authentication | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 6
6. Create a log-in page | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 4
7. Create eligibility function | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. Create Main page functionality | 8 | 0 | 0 | 0 | 3 | 0 | 0 | 2 | 2 | 7
9. Create Review page | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3
10. Create an Admin Panel | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
Actual Remaining Effort | 40 | 36 | 33 | 31 | 27 | 24 | 18 | 10 | 6
Estimated Remaining Effort | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0