## Study Plan App - Burndown Chart
Task | Start Pts | Pts Done Sprint 1.0 | Pts Done Sprint 1.5 | Pts Done Sprint 2.0 | Pts Done Sprint 2.5 | Pts Done Sprint 3.0 | Pts Done Sprint 3.5 | Pts Done Sprint 4.0 | Pts Done Sprint 4.5 | Total Pts Done
1. Create Database | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4
2. Create Documentation | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3
3. Create the Main page GUI. | 7 | 1 | 1 | 1 | 0 | 1 | 2 |  |  | 6
4. Create a save function. | 4 | 0 | 0 | 0 | 0 | 1 |  |  |  | 1
5. Create Single sign-on authentication | 6 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 3
6. Create a log-in page | 4 | 0 | 0 | 0 | 0 | 1 | 2 |  |  | 3
7. Create eligibility function | 2 | 0 | 0 | 0 | 0 |  |  |  |  | 0
8. Create Main page functionality | 8 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 3
9. Create Review page | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1
10. Create an Admin Panel | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1
Actual Remaining Effort | 38 | 34 | 31 | 29 | 25 | 22 | 15 | 15 | 15
Estimated Remaining Effort | 38 | 33.25 | 28.5 | 23.75 | 19 | 14.25 | 9.5 | 4.75 | 0